## Introduction
Project Tracker
Introduction: This tracker provides a framework to allocate lead responsibility to specific team members across tasks and deliverables within each of the four indicators (EC, OC, Water Use and IEQ). Responsible team members should ensure their tasks are kept up to date within the tracker so it becomes the Single Source of Truth for status updates and information as a project moves through the workstages. It also includes the Level(s) statement and reporting templates necessary for completion of level 1 (L1) and level 2 (L2) reporting. The Carbon Opportunities tab can be used to register possibilities and ideas for follow up that emerge at team meetings.
There are three tracker tabs: Embodied and Operational Carbon are combined into the Carbon Task Tracker as there are overlaps between these two indicators. There are also Tracker Tabs for Water Tasks and IEQ Tasks. Each tracker tab reflects the tasks and deliverables as described in the framework and guidance. They can be used to clarify responsibilities and provide contact details within the team. Feel free to edit the roles in the Responsibilites Matrix to reflect the roles within the design team. Use of this type of tracker enables you to document progress and completion of actions at each stage and report this during regular project team meetings.
The L1 statements should be used at Workstage 1 for each of the indicators. The statements are taken from the Level(s) indicator manuals. They are designed to challenge the core team to provide details of the strategic aims and ambitions of the project. By completing these statements, the core team sets the direction for the progress of the project at the earliest stage.
The L2 Reports should be used at later workstages as more details become available, until there is a finalised report for each indicator based on the developed design.
Upon completion of the project the L2 reports should be updated with actual information from the building in operation to provide an L3 report on actual performance to compare with the design performance of L2.
All Level(s) indicator manuals are available at
https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
This tracker is based on an original concept by Grimshaw; the Minoro project is availabe at:
https://www.minoro.org/

## Carbon Opportunities
Carbon Opportunities Register
ID | Building Area / Element | Opportunity Description | Potential Impacts |  |  |  |  | Associated Risks | Mitigation Measures | Follow Up Actions | Owner[s] | Due Date | Status
|  |  | Embodied Carbon | Operational Energy | Programme | Capital Cost | Life Cycle Cost
Carbon Opportunities Register can be used to register possibilities and ideas for follow up that emerge at team meetings.

## CarbonTaskTracker
= Embodied Carbon
= Operational Carbon
= Both
Carbon Tasks Tracker
Key Actions |  | Responsibility Matrix | [12 empty] | Action Owner | Deliverable | Risks | Status % | Due date | Progress Notes
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer |  | Deliverable
|  | Roles: |  | L = Lead |  |  |  | S = Support
STAGE 1: Inception & General Services
1.01 | Assign responsibilities for all tasks and confirm | [13 empty] | Name & email |  |  | 100 | bar: Responsibility Matrix 1 to Responsibility Matrix 2
1.02 | Question the brief and prioritise existing buildings
1.03 | Establish WLC Goals and the method of measurement | [14 empty] | Lifecycle GWP assessment method selected & targets agreed
1.04 | Brief the client on the benefits and co-benefits of a lower carbon approach | [14 empty] | Client aware of benefits of low carbon approach
1.05 | Site Selection
1.06 | Familiarise the EU Level(s) Framework
1.07 | Complete L1 statement for Level(s) indicator 1.2 | [14 empty] | Level 1 statement for Indicator 1.2 created and signed by architect and client
1.08 | Establish EC and OC targets for a later L2 assessment
1.09 | Discuss initial preferences for low -carbon materials.
1.1 | Consider flexible floor plans and/or modular design
1.11 | Consider design for disassembly
1.12 | Commit to net zero operational carbon vision
1.13 | Explain the co-benefits of low-energy building
1.14 | Discuss Operational energy management strategies | [14 empty] | Operational Carbon Target and modelling tool for measurement confirmed.
1.15 | Complete L1 statement for Level(s) Indicator 1.1 | [14 empty] | Level 1 statement for Indicator 1.1 created and signed by architect and client
1.16 | Establish operational target and method of measurement | [14 empty] | A report setting out the proposed operational energy targets
1.17 | Select site and orientation for passive gains
1.18 | Define energy flexibility strategy
STAGE 2: Outline Proposals
2.01 | Explore different design options with a focus on minimising embodied carbon | [14 empty] | Initial report setting out various design and structural options, including comparison of conventional materials and low carbon innovative materials
2.02 | Draw up preliminary material and component palette
2.03 | Carry out early conceptual WLC Assessment
2.04 | Consider orientation and window size/placement for PV and optimum passive gains. | [14 empty] | A short report on optimising energy strategy based on specific location, orientation and form factor
2.05 | Aim for the most efficient Form Factor the brief allows
2.06 | Model early concept
2.07 | Consider hot water use and heat losses within layout
STAGE 3: Scheme Design
3.01 | Design, assess, iterate | [14 empty] | Interim stage embodied carbon calculation based on generic data which aligns with target
3.02 | Reduce hotspots based on assessment results – optimise.
3.03 | Design for D&D, replacement and even relocation
3.04 | Review Form Factor in more detail | [14 empty] | Form factor optimisation report
3.05 | Take a Fabric First (FF) approach - Emphasise airtightness | [14 empty] | Air-tightness strategy and insulation continuity report
3.06 | FF - Limit cold bridging
3.07 | FF – Consider solar gains to reduce heat demand | [14 empty] | Solar gain and shading analysis
3.08 | FF – Consider shading & overheating in the modelling
3.09 | FF- Consider glazing ratio alongside orientation
3.1 | FF – Develop ventilation & MVHR strategy | [14 empty] | Report on ventilation and heating strategy
3.11 | Create more detailed models for performance comparison | [14 empty] | Report on proposal detailing the energy use patterns of the design based on an unrefined model
3.12 | Refine technical solutions for energy flexibility
STAGE 4: Detail Design / Building Regulations
4.01 | Identify low carbon materials and specify their performance
4.02 | Finalise as designed L2 assessment using specified performance | [14 empty] | An as designed WLCA at Level 2 based on quantities of materials and assumptions in line with Level(s) indicator 1.2 that meets the target for embodied carbon.
4.03 | Include on-site waste management programme | [14 empty] | Construction Waste Management Plan (CWMP) is agreed
4.04 | Optimise and fine-tune the FF elements discussed in Workstage 3 | [14 empty] | Renewable energy integration report
4.05 | Energy Efficient Solutions Integration - Heat Pumps, PV, etc. | [14 empty] | Heat pump specification and sizing report
4.06 | Consider energy-efficient solutions – thermal & battery options, etc.
4.07 | Consider energy-efficient lighting
4.08 | Specify the right size of equipment | [14 empty] | Equipment sizing and load calculation report
4.09 | Finalise the energy model | [14 empty] | Report with the results of a complete energy model
STAGE 5: Production Information
5.01 | Produce all drawings and specification. | [14 empty] | Accurate assessment of building using detailed BOQ to IQSS3 has been created. WLC meets the specified target and forms part of the contractual performance requirements in tender.
5.02 | Monitor Value Engineering for impact on WLC
5.03 | Include Construction Waste Management Plan (CWMP)
5.04 | Finalise main contractor reporting responsibilities | [14 empty] | The final agreed performance target is provided in KgCO2e together with the Bill of Quantities, specification of all quantities and carbon performance of materials on which they are based.
5.05 | Finalise the FF elements refined in Workstage 4
5.06 | Work out the unregulated energy loads | [14 empty] | Schedule of high-efficiency white goods,other non regulated load calculations demonstrating alignment with operational energy target
5.07 | Check regulated and unregulated loads are within the target. | [14 empty] | Specifications of right size equipment
5.08 | Finalise Renewable Energy Systems | [14 empty] | Renewable energy system documentation
5.09 | Develop contractor performance clauses for tender
STAGE 6: Tender Action
6.01 | Award Contract | [14 empty] | Contractor with required experience is selected. Recalculation of WLCA if any value engineering suggestions are accepted.
6.02 | Emphasise future assessment requirements | [14 empty] | Final contract documents include performance targets based on BoQ and material GWP performance specifications.
6.03 | Monitor post tender Value Engineering
6.04 | Appoint a contractor with experience on low energy design and delivery
6.05 | Include POE requirements in contract
6.06 | Ensure that energy calculations for provisional EPC calculation are complete and issued | [14 empty] | Final calculations of expected performance based on specified equipment
6.07 | Monitor Value Engineering decisions for impact
STAGE 7: Project Planning
7.01 | Pre-commencement meeting: Remind contractor of data obligations
7.02 | Ensure any amendments to specifications for final construction do not impact on WLC. | [14 empty] | GWP Target tracking Protocol in place between contractor and design team for approval of substitutions and remeasurement and included on site meeting agenda.
7.03 | Confirm energy performance by re-checking the design | [14 empty] | Energy performance verification report
7.04 | Ensure that the right personnel are in place including contractor quality champion | [14 empty] | Material procurement documentation
7.05 | Ensure compliance with regulations and energy code
7.06 | Check any value engineering does not compromise performance | [14 empty] | Compliance report
7.07 | Monitoring Systems Design and Specifications
STAGE 8: Operations on-site and Completion
8.01 | Monitor construction activities to ensure adherence to WLC reduction strategies. | [14 empty] | All data from purchase orders, invoicing, rental agreements etc. collected and stored. EPDs for product substitution are recorded.
8.02 | Implement the CWMP and track waste diversion rates
8.03 | Conduct the As-Built Lifecycle GWP Assessment | [14 empty] | Final WLC calculation based on actual quantities
8.04 | Performance testing – air tightness | [14 empty] | Air tightness test report
8.05 | Domestic Hot Water system testing | [14 empty] | DHW system testing report
8.06 | Ventilation and MVHR testing | [14 empty] | Ventilations and MVHR testing report(s)
8.07 | Heating and cooling system efficiency testing | [14 empty] | Heating and Cooling system performance report
8.08 | Thermal imaging to highlight any inefficiencies | [14 empty] | Thermal imaging survey report
8.09 | Monitor implementation of energy flexibility measures | [14 empty] | Energy flexibility report
Post Occupancy / Completion
9.01 | Ensure the plan for future deconstruction and material reuse or recycling is stored safely for future use. | [14 empty] | Operational and disassembly guidance manuals are developed and distributed to stakeholders
9.02 | Recommendations for Equipment | [14 empty] | Equipment recommendations
9.03 | Energy Metering | [14 empty] | Energy metering report
9.04 | Develop a user manual for efficient use | [14 empty] | User manual
9.05 | Adjust any BEMS to optimise use | [14 empty] | BEMS optimisation report
9.06 | Inform managers and occupants on energy flexibility
9.07 | Conduct audits and preventative maintenance | [14 empty] | Audits and preventative maintenance schedules

## CarbonDeliverablesTracker (hidden)
= Embodied Carbon
= Operational Carbon
= Both
Carbon Deliverables Tracker
Deliverable |  | Responsibility Matrix | [12 empty] | Action Owner | Risks | Status % | Due date | Progress notes or links to delivered documents
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer
|  | Roles: |  | L = Lead |  |  |  | S = Support
5
STAGE 0: Strategy
0.01 | [14 empty] | Owner@Minoro.com | 100 | 2024-01-01 |  | Update and reissue
0.02 | [15 empty] | 100
0.03 | [15 empty] | 50
0.04 | [15 empty] | 60
0.05 | [15 empty] | 30
0.06 | [15 empty] | 20
0.07 | [15 empty] | 10
STAGE 1: Inception & General Services
1.01 | Client aware of benefits of low carbon approach | [13 empty] | Name & email |  | 100 | bar: Responsibility Matrix 1 to Responsibility Matrix 2
1.02 | Level 1 statement for Indicator 1.2 created and signed by architect and client
1.03 | Lifecycle GWP assessment method selected & targets agreed
1.04 | A report setting out the proposed operational energy targets
1.05 | Level 1 statement for Indicator 1.1 created and signed by architect and client
1.06 | Operational Carbon Target and modelling tool for measurement confirmed.
STAGE 2: Outline Proposals
2.01 | Initial report setting out various design and structural options, including comparison of conventional materials and low carbon innovative materials
2.02 | A short report on optimising energy strategy based on specific location, orientation and form factor
STAGE 3: Scheme Design
3.01 | Interim stage embodied carbon calculation based on generic data which aligns with target
3.02 | Report on proposal detailing the energy use patterns of the design based on an unrefined model
3.03 | Form factor optimisation report
3.04 | Air-tightness strategy and insulation continuity report
3.05 | Solar gain and shading analysis
3.06 | Report on ventilation and heating strategy
STAGE 4: Detail Design / Building Regulations
4.01 | An as designed WLCA at Level 2 based on quantities of materials and assumptions in line with Level(s) indicator 1.2 that meets the target for embodied carbon.
4.02 | Construction Waste Management Plan (CWMP) is agreed
4.03 | Report with the results of a complete energy model
4.04 | Renewable energy integration report
4.05 | Heat pump specification and sizing report
4.06 | Equipment sizing and load calculation report
STAGE 5: Production Information
5.01 | Accurate assessment of building using detailed BOQ to IQSS3 has been created. WLC meets the specified target and forms part of the contractual performance requirements in tender.
5.02 | The final agreed performance target is provided in KgCO2e together with the Bill of Quantities, specification of all quantities and carbon performance of materials on which they are based.
5.03 | Specifications of right size equipment
5.04 | Schedule of high-efficiency white goods,other non regulated load calculations demonstrating alignment with operational energy target
5.05 | Renewable energy system documentation
STAGE 6: Tender Action
6.01 | Contractor with required experience is selected. Recalculation of WLCA if any value engineering suggestions are accepted.
6.02 | Final contract documents include performance targets based on BoQ and material GWP performance specifications.
6.03 | Final calculations of expected performance based on specified equipment
STAGE 7: Project Planning
7.01 | GWP Target tracking Protocol in place between contractor and design team for approval of substitutions and remeasurement and included on site meeting agenda.
7.02 | Energy performance verification report
7.03 | Material procurement documentation
7.04 | Compliance report
STAGE 8: Operations on-site and Completion
8.01 | All data from purchase orders, invoicing, rental agreements etc. collected and stored. EPDs for product substitution are recorded.
8.02 | Final WLC calculation based on actual quantities
8.02 | Air tightness test report
8.03 | DHW system testing report
8.04 | Ventilations and MVHR testing report(s)
8.05 | Heating and Cooling system performance report
8.06 | Thermal imaging survey report
8.07 | Energy flexibility report
Post Occupancy / Completion
9.01 | Operational and disassembly guidance manuals are developed and distributed to stakeholders
9.02 | Energy metering report
9.03 | User manual
9.04 | BEMS optimisation report
9.05 | Equipment recommendations
9.06 | Audits and preventative maintenance schedules

## 1.1 L1 Energy Statement
Ind. 1.1 Levels L1
Level 1 design concept | Brief description | Addressed? (Yes/No) | How has it been incorporated into the building design concept? (Provide a brief description)
1.Minimum energy performance requirements and Near ZeroEnergy Building (NZEB) design |  Minimise the heating, cooling and lighting energy use of the building by: - (for new buildings) designing and specifying a high performance and air-tight building fabric. - Designing and specifying high performance heating, ventilation, cooling and (fixed) lighting systems. - (for major renovations) detailing and specifying high performance improvements to the existing building fabric. - Designing and specifying high performance heating, ventilation, cooling and (fixed) lighting systems.  Using renewable energy technologies to, as far as possible, supply energy to the building.
2. Site specific design | In designing a new building, or in planning a major renovation of an existing building, take into account:  The climatic conditions of the site in order to minimise heating, cooling, domestic hot water, ventilation and lighting needs and to inform the specification of noncombustion renewable energy technologies. Steps that can be taken include: - Reference to local weather data in order to understand better the distinct seasonal, monthly, weekly and diurnal conditions. - Reference to information about any localised microclimate conditions, such as prevailing winds, the urban heat island effect and air pollution levels. In this way, the physical design, elevations and servicing can be designed to respond to the local climate, including the potential for passive heating/cooling, intelligent structures, high yield renewables and use of daylighting. This aspect has a strong interaction with indicators 4.2 and 4.3, which address thermal comfort and lighting respectively.
3. Renovation specific design | In seeking to renovate a building, use information gathered in a baseline survey to adapt the improvements to the performance and conditions of the existing building, taking into account:  The construction of the original building, including the building envelope and structure.  Existing technical services, including heating, cooling, domestic hot water, ventilation and lighting.  How the orientation and floor layout influences patterns of climatic exposure, daylighting and ventilation. Information obtained from prior occupants may also yield useful information about the buildings performance.
4. High quality building fabric and services | Minimise the potential for gaps between design and actual performance by ensuring that the building fabric and technical services are designed, specified, constructed and installed with the necessary attention to detail and quality. This could include a focus on:  The air tightness and thermal integrity of the building envelope, including the continuity of insulation and junctions with windows, doors and balconies.  The functional performance of HVAC7 systems, including the design of distribution systems and the setup of equipment.
5. Smart monitoring and control systems | Identify opportunities to install intelligent systems that can:  Provide users and building managers with timely information about the buildings energy use, whilst also allowing them to learn how to meet occupier energy needs with less energy.  Be used to maximise the potential for self-consumption of renewable energy generated by the building.
Adapted from Level(s) indicator 1.1: Use stage energy performance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-11/UM3_Indicator_1.1_v1.2_34pp_clean_15.07.2021.pdf

## 1.1 L2 Energy Report
Ind. 1.1 Levels L2 / L3
Supporting Information
Level 2 reporting item | Information to provide (select/delete as appropriate) |  |  |  |  | Level 3 reporting item |  | Information to provide (select/delete as appropriate)
Type of assessment | Building permit, as-built (calculated) EPC or tailored assessment |  |  |  |  | Type of assessment |  | Measured EPC or other type of corrected (measured) assessment
Calculation method | Specify the method and any software tools used |  |  |  |  | Sampling period |  | How long after completion of the building and for how many years?
| The time step for the data used by the method e.g. monthly, daily, hourly |  |  |  |  | Corrections applied |  | Please detail any corrections applied to the data and according to which standard.
[6 empty] | Primary energy factors |  | Please identify the calculation method from which the factors used are taken
Delivered energy use assessment for the building
Building service | Energy need | System efficiency 1 | Energy carrier 2 | Delivered energy per energy carrier | Non renewable primary energy factor 3 |  | Renewable primary energy factor 3 |  | Total primary energy factor 3
Column1 | kWh/yr | Decimal | Free text | kWh/yr | Decimal factor | kWh /yr | Decimal factor | kWh/ yr | Decimal factor2 | kWh / yr
Heating
Cooling
Ventilation
Hot water
Lighting
Other (please specify) 4
Exported renewable energy 5 | n/a | n/a
Total | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
1. The efficiency with which delivered energy is converted into needed energy. For example, if a boiler converts 85% of the calorific value of a fuel into heat in water coming out of the tap or shower, the system efficiency would be 0.85. Dividing the energy need by the system efficiency will produce the delivered energy result (delivered energy can never be lower than the energy needed). 2. For example, energy carriers from distant sources: solid, liquid or gaseous fossil fuels; solid, liquid or gaseous biofuels or grid electricity. From nearby sources: district heating or district cooling. From onsite sources: electricity from PV panels, electricity from wind turbines, heat from solar thermal, geothermal or aerothermal. In the cases where more than one energy carrier is used for the same building system (e.g. hot water from a gas boiler and from onsite solar thermal) two rows should be made for hot water, one for each energy carrier. There must always be a dedicated row for each energy carrier for any given service. 3. Any given energy carrier may have a non-renewable factor and a renewable factor, or just one of the two. These factors may be greater than, equal to, or less than 1, although the combined total of non-renewable and renewable primary energy factors for a given energy carrier cannot be less than 1. 4. If the methodology requires other energy needs to be accounted for, or the user simply wants to do this, then one row should be used for each “other” energy service. 5. When making the entry for delivered energy for any exported renewable energy from the building, a negative number should be used.
Adapted from Level(s) indicator 1.1: Use stage energy performance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-11/UM3_Indicator_1.1_v1.2_34pp_clean_15.07.2021.pdf

## 1.2 L1 Lifecycle GWP Statement
Ind. 1.2 Levels L1
Level 1 design concept | Brief description | Addressed? (Yes/No) | How has it been incorporated into the building design concept? (Provide a brief description)
1. Efficient building shape and form | Minimise the surface area to volume ratio of a building and individual residential units, as well as its height, in order to improve material efficiency and minimise energy use.
2. Optimised NZEB construction | Consider the potential trade-off between reducing CO2 emissions in the use stage to achieve NZEB performance levels and the embodied energy CO2 emissions associated with the manufacture of higher performance insulation, façade and wall systems, windows, structural thermal mass and renewable energy technologies.
3. Optimised material utilisation and circular value | Consider the feasibility of reusing the structure of an existing building or for optimising the structural design of a new building in order to minimise material use. Consider options to minimise or even design out waste generated during product manufacturing, construction on-site in order to optimise the utilisation of materials on a construction site.
4. Extending building and component service lives | Consider the options to extend the lifespan of significant building components and to minimise the number of replacement and renovation cycles.
5. Design for adaptability | Consider the potential of the building design to adapt and be flexible to changing market and occupier needs in the future so as to extend the life of the building, including its structure and main elements.
6. Design for deconstruction | Consider how the building design and information records about the building’s material bank can facilitate future end of life deconstruction in order to recover materials for re-use and recycling.
Adapted from Level(s) indicator 1.2: Life cycle Global Warming Potential (GWP) User manual: introductory briefing, instructions and guidance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full Manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_Indicator_1.2_v1.1_37pp.pdf

## 1.2 L2 Lifecycle GWP Report
Ind. 1.2 Levels L2
Indicator | Unit | Product (A1-3) | Construction process (A4-5) | Use stage (B1-7) | End of life (C1-4) | Benefits and loads beyond the system boundary (D)
(1) GWP - fossil | kg CO2 eq
(2) GWP - biogenic | kg CO2 eq
- GWP – GHGs (1+2) kg CO2 eq | kg CO2 eq
(3) GWP – land use and land use change | kg CO2 eq
- GWP – overall (1+2+3) kg CO2 eq | kg CO2 eq
Impacts refer to the use of 1 m2 of useful internal floor per year for a default reference study period of 50 years.
Use the INDICATE LifecycleGWP calculator workbook saved here to do the calculations: |  |  |  | INDICATE LIFECYCLE GWP CALCULATOR
Adapted from Level(s) indicator 1.2: Life cycle Global Warming Potential (GWP) User manual: introductory briefing, instructions and guidance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_Indicator_1.2_v1.1_37pp.pdf

## WaterTaskTracker
= Water Task
Water Tasks Tracker
Action |  | Responsibility Matrix | [12 empty] | Action Owner | Deliverable | Risks | Status % | Due date | Progress notes
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer
|  | Roles: |  | L = Lead |  |  |  | S = Support
STAGE 1: Inception & General Services
1.01 | Assign responsibilities for all tasks and confirm | [13 empty] | Name & email |  |  | 100 | bar: Responsibility Matrix 1 to Responsibility Matrix 2
1.02 | Confirm any proposals for landscaped areas and irrigation requirements
1.03 | Review of water efficient sanitary devices and fittings
1.04 | Examine the potential to use non-potable water to substitute for potable water demand
1.05 | Evaluate the advantages of metering | [14 empty] | The agreed targets for water efficiency are included in the brief
STAGE 2: Outline Proposals
2.01 | Ensure landscaped areas are water efficient | [16 empty] | -
2.02 | Review proposed sanitary devices and fittings | [16 empty] | -
2.03 | Examine the potential to use non-potable water to substitute for potable water demand | [16 empty] | -
2.04 | Include Metering Plan | [14 empty] | Short report on how water efficiency is being integrated into the proposal. |  | -
STAGE 3: Scheme Design
3.01 | Specify water efficient sanitary devices and fittings | [16 empty] | -
3.02 | Examine the use of non-potable water to substitute for potable water demand
3.03 | Develop further the design for landscaped areas with non-potable water use
3.04 | Develop the plan for Metering and sub-metering within the building
3.05 | Ensure the designed water pressure is optimised for maximum efficiency | [14 empty] | Updated report on how water efficiency is being integrated into the proposal
STAGE 4: Detail Design / Building Regulations
4.01 | Confirm the efficiency related specification | [14 empty] | Specification of water efficient sanitary ware |  | -
4.02 | Examine the potential to use-non potable water | [16 empty] | -
4.03 | Develop any specification for greywater or rainwater harvesting systems
4.04 | Develop the specification for landscaped areas with non-potable water use. | [14 empty] | Landscape design developed without use of potable water
4.05 | Develop the specification for Metering and sub-metering within the building. | [14 empty] | A calculation showing that the target is met with the calculations
STAGE 5: Production Information
5.01 | Specification of water efficient sanitary devices and fittings | [14 empty] | All specifications for water fittings are included in specifications |  | -
5.02 | Detail design for substitution measures for potable water demand: | [16 empty] | -
5.03 | Produce the drawings and the specification for landscaped areas with no potable water use. | [14 empty] | All specifications for landscaping are included in specifications
5.04 | Produce the drawings and the specification for Metering and sub-metering within the building.
STAGE 6: Tender Action
6.01 | Ensure that water efficiency measures are not removed | [14 empty] | The Performance targets for water efficiency are included as a contractual requirement |  | -
STAGE 7: Project Planning
7.01 | Ensure any changes to construction specifications and drawings do not impact targets | [14 empty] | Final construction specifications and drawings retain targets |  | -
STAGE 8: Operations on-site and Completion
8.01 | Confirm the specified system has been installed correctly | [14 empty] | Commissioning report on all installed potable water substitution measures and documents for maintenance manual |  | -
8.02 | Test flow rates | [14 empty] | Checklist confirming flow rates for all installed sanitary fittings |  | -
8.03 | Review landscaped areas against the drawings | [14 empty] | Text for maintenance manual for landscaping on low water use features |  | -
8.04 | Review metering against the specification | [14 empty] | Text for Home User manual (for residential) explaining water efficiency measures and their benefit in terms of cost and energy efficiency |  | -
Post Occupancy / Completion
9.01 | Check that water efficient measures are operating correctly
9.02 | If non-potable water substitutes installed ensure that systems are operating correctly
9.03 | Confirm that non-potable water is being used for irrigation if required and any planting is establishing
9.04 | Develop monitoring plan to ensure that systems continue to operate as specified | [14 empty] | Ongoing Verification: Collect data from water meters to assess actual performance

## WaterDeliverablesTracker (hidden)
= Water Task
Water Deliverables Tracker
Action |  | Responsibility Matrix | [12 empty] | Action Owner | Risks | Status % | Due date | Progress notes or links to delivered documents
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer
|  | Roles: |  | L = Lead |  |  |  | S = Support
5
STAGE 0: Strategy
0.01 | [14 empty] | Owner@Minoro.com | 100 | 2024-01-01 |  | Update and reissue
0.02 | [15 empty] | 100
0.03 | [15 empty] | 50
0.04 | [15 empty] | 60
0.05 | [15 empty] | 30
0.06 | [15 empty] | 20
0.07 | [15 empty] | 10
STAGE 1: Inception & General Services
1.01 | The agreed targets for water efficiency are included in the brief | [13 empty] | Name & email |  | 1 | bar: Responsibility Matrix 1 to Responsibility Matrix 2
STAGE 2: Outline Proposals
2.01 | Short report on how water efficiency is being integrated into the proposal. | [15 empty] | -
STAGE 3: Scheme Design
3.01 | Updated report on how water efficiency is being integrated into the proposal | [15 empty] | -
STAGE 4: Detail Design / Building Regulations
4.01 | Specification of water efficient sanitary ware | [15 empty] | -
4.02 | A calculation showing that the target is met with the calculations | [15 empty] | -
4.03 | Landscape design developed without use of potable water
STAGE 5: Production Information
5.01 | All specifications for water fittings are included in specifications | [15 empty] | -
5.02 | All specifications for landscaping are included in specifications | [15 empty] | -
STAGE 6: Tender Action
6.01 | The Performance targets for water efficiency are included as a contractual requirement | [15 empty] | -
STAGE 7: Project Planning
7.01 | Final construction specifications and drawings retain targets | [15 empty] | -
STAGE 8: Operations on-site and Completion
8.01 | Checklist confirming flow rates for all installed sanitary fittings | [15 empty] | -
8.02 | Commissioning report on all installed potable water substitution measures and documents for maintenance manual | [15 empty] | -
8.03 | Text for maintenance manual for landscaping on low water use features | [15 empty] | -
8.04 | Text for Home User manual (for residential) explaining water efficiency measures and their benefit in terms of cost and energy efficiency | [15 empty] | -
Post Occupancy / Completion
9.01 | Ongoing Verification: Collect data from water meters to assess actual performance

## 3.1 L1 Water Statement
Ind. 3.1 Levels L1
Level 1 design concept | Brief description | Addressed? (Yes/No) | How has it been incorporated into the building design concept? (provide a brief description)
1. Specification of water efficient sanitary devices and fittings | Consider the ranges of performance for different choices of sanitary devices and fittings (e.g. tap and showerhead flow rates in L/min, toilet flush volumes in L/flush etc.). Consult national or international labelling schemes.
2. Consider the importance of water scarcity in the river basin where the building is located | Cross-check water exploitation index (WEI+) data for the river basin in which the building will be located and compare this to other European river basins. Any average summer WEI+ value >20% should be flagged as water scarcity being a definite concern.
3. Potential of rainwater harvesting and greywater reuse | Consider the potential of the building and site for: - rainwater harvesting (i.e. look at collection area available and rainfall patterns) - greywater reuse (i.e. consider relevant uses such as toilet flushing and irrigation together with relevant sources of greywater such as showers and bathroom wash basins).
4. Consider water efficiency aspects in any vegetated areas | When assessing whether or not to have vegetated areas at the building site, consider how the following aspects can reduce irrigation water demand: - the choice of low water demand plants - the use of efficient irrigation techniques - staging of vegetation and other factors that can create microenvironments that reduce evaporation rates.
5. Consider a metering plan | To install multiple meters onsite to better monitor where water consumption is happening in the building, to better quantify the significance of irrigation and any contributions of harvested rainwater and reused greywater to total water consumption.
Adapted from Level(s) indicator 3.1: Use stage water consumption User manual: introductory briefing, instructions and guidance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_Indicator_3.1_v1.1_31pp.pdf

## 3.1 L2 Water Report
Ind. 3.1 Levels L2
Use the Level(s) water calculator available at the below link for full calculation and result:
https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_indicator_3.1_excel_v2.1.xlsx
Full instructions are given in Levels indicator 3.1 Use Stage Water consumption Manual:
https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_Indicator_3.1_v1.1_31pp.pdf
All Level(s) manuals available at:
https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents

## IEQTaskTracker
= IEQ Task
IEQ Tasks Tracker
Deliverable |  | Responsibility Matrix | [12 empty] | Action Owner | Deliverable | Risks | Status % | Due date | Progress notes / Links
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer |  | De
|  | Roles: |  | L = Lead |  |  |  | S = Support
STAGE 1: Inception & General Services
1.01 | Assign responsibilities for all tasks and confirm | Responsibility Matrix 1: L; Responsibility Matrix 2: S; Responsibility Matrix 5: s | Name & email |  |  | 0
1.02 | Establish health and wellbeing objectives | [14 empty] | Health and Well-being Report
1.03 | Site selection and environmental context | [14 empty] | Environmental context assessment
1.04 | Biophilic & inclusive design
1.05 | Discuss client’s needs and future-proofing
1.06 | Complete L1 of Level(s) Indicator 4.1. – Indoor Environmental Quality. | [14 empty] | Complete 4.1 L1 IEQ Statement (see Tab)
STAGE 2: Outline Proposals
2.01 | Inspection of property in renovation cases | [16 empty] | -
2.02 | Design solutions for identified problematic areas in renovation cases
2.03 | Check for asbestos in buildings built pre-2000
2.04 | Design the building fabric and ventilation system | [14 empty] | Ventilation concept report
2.05 | Building design choices
2.06 | Material selection
2.07 | Mitigation for extreme weather | [16 empty] | -
2.08 | Integrate outdoor spaces | [16 empty] | -
STAGE 3: Scheme Design
3.01 | Optimising building orientation and form | [16 empty] | -
3.02 | Overheating assessment | [16 empty] | -
3.03 | Consider Daylight and Acoustic design
3.04 | Review ventilation design | [14 empty] | Health and well-being strategy
3.05 | Review material selection | [14 empty] | Short strategic report
STAGE 4: Detail Design / Building Regulations
4.01 | Detailed environmental design
4.02 | Prepare documents for Level(s) checklist under indicator 4.1 for IAQ | [14 empty] | Report showing IAQ and ventilation design concepts using Level(s) L2 reporting format |  | -
4.03 | Finalise ventilation strategy | [14 empty] | updated calculations |  | -
4.04 | Finalise thermal comfort and daylight strategy | [14 empty] | updated calculations
4.05 | Finalise acoustic comfort and accessibility strategy | [14 empty] | updated calculations
4.06 | Finalise material selection | [14 empty] | updated calculations
STAGE 5: Production Information
5.01 | Report and documentation | [14 empty] | Report with specifications. Risk register in MC preliminaries |  | -
STAGE 6: Tender Action
6.01 | Contractor selection | [14 empty] | Performance targets and testing are included in the contract sum |  | -
STAGE 7: Project Planning
7.01 | Ensure VE changes to tender specifications do not impact the intended design | [16 empty] | -
7.02 | Meeting with contractor to ensure that protocols for product substitutions are agreed | [14 empty] | Agreed protocols with contractor
STAGE 8: Operations on-site and Completion
8.01 | Ensure plan for quality of installation of radon barrier | [16 empty] | -
8.02 | In-situ measurement of the indoor concentration of target pollutants | [16 empty] | -
8.03 | Functional performance testing of ventilation filters | [16 empty] | -
8.04 | Check whether the ventilation strategy can be linked to real-life monitoring of IAQ | [16 empty] | -
8.05 | If periodic monitoring of VOC and particulate emissions is undertaken, consider the most representative locations to install sensors/take measurements | [16 empty] | -
8.06 | Verify the as-built fabric and services align with the original design specifications | [14 empty] | All data sheets of materials used are to be provided. |  | -
8.07 | 3rd party commissioning of ventilation systems | [14 empty] | Commissioning certificates for each separate building/apartment/unit/dwelling are provided in compliance with Part F |  | -
Post Occupancy / Completion
9.01 | In-situ pollutant measurement
9.02 | Functional performance testing of ventilation filters
9.03 | In-situ pollutant measurement during occupation
9.04 | In-situ measurement of CO2 and relative humidity
9.05 | Carry out a radon test | [14 empty] | Report using Level(s) L3 reporting format.

## IEQDeliverablesTracker (hidden)
= IEQ Task
IEQ Deliverables Tracker
Deliverable |  | Responsibility Matrix | [12 empty] | Action Owner | Risks | Status % | Due date | Progress notes or links to delivered documents
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Client / Owner | Architect | Ecologist | Energy Modeller | Facilities Manager | Landscape Architect | Life Cycle Assessment Consultant | Main Contractor | Mechanical Electrical Services Engineer | Project Manager | Quantity Surveyor | Specialist Consultant | Structural Engineer
|  | Roles: |  | L = Lead |  |  |  | S = Support
5
STAGE 0: Strategy
0.01 | [14 empty] | Owner@Minoro.com | 100 | 2024-01-01 |  | Update and reissue
0.02 | [15 empty] | 100
0.03 | [15 empty] | 50
0.04 | [15 empty] | 60
0.05 | [15 empty] | 30
0.06 | [15 empty] | 20
0.07 | [15 empty] | 10
STAGE 1: Inception & General Services
1.01 | Assign responsibilities for all tasks and confirm | [13 empty] | Name & email |  | 0 | bar: Responsibility Matrix 1 to Responsibility Matrix 2
1.02 | Establish health and wellbeing objectives
1.03 | Site selection and environmental context
1.04 | Biophilic & inclusive design
1.05 | Discuss client’s needs and future-proofing
STAGE 2: Outline Proposals
2.01 | Inspection of property in renovation cases | [15 empty] | -
2.02 | Design solutions for identified problematic areas in renovation cases
2.03 | Check for asbestos in buildings built pre-2000
2.04 | Design the building fabric and ventilation system
2.05 | Building design choices
2.06 | Material selection
2.07 | Mitigation for extreme weather | [15 empty] | -
2.08 | Integrate outdoor spaces | [15 empty] | -
STAGE 3: Scheme Design
3.01 | Overheating assessment | [15 empty] | -
3.02 | Consider Daylight and Acoustic design
3.03 | Review ventilation design
3.04 | Review material selection
STAGE 4: Detail Design / Building Regulations
4.01 | Prepare documents for Level(s) checklist under indicator 4.1 for IAQ | [15 empty] | -
4.02 | Finalise ventilation strategy | [15 empty] | -
4.03 | Finalise thermal comfort and daylight strategy
4.04 | Finalise acoustic comfort and accessibility strategy
4.05 | Finalise material selection
STAGE 5: Production Information
5.01 | Report and documentation | [15 empty] | -
STAGE 6: Tender Action
6.01 | Contractor selection | [15 empty] | -
STAGE 7: Project Planning
7.01 | Ensure VE changes to tender specifications do not impact the intended design | [15 empty] | -
7.02 | Meeting with contractor to ensure that protocols for product substitutions are agreed
STAGE 8: Operations on-site and Completion
8.01 | Ensure plan for quality of installation of radon barrier | [15 empty] | -
8.02 | In-situ measurement of the indoor concentration of target pollutants | [15 empty] | -
8.03 | Functional performance testing of ventilation filters | [15 empty] | -
8.04 | Check whether the ventilation strategy can be linked to real-life monitoring of IAQ | [15 empty] | -
8.05 | If periodic monitoring of VOC and particulate emissions is undertaken, consider the most representative locations to install sensors/take measurements | [15 empty] | -
8.06 | Verify the as-built fabric and services align with the original design specifications | [15 empty] | -
8.07 | 3rd party commissioning of ventilation systems | [15 empty] | -
Post Occupancy / Completion
9.01 | In-situ pollutant measurement
9.02 | Functional performance testing of ventilation filters
9.03 | In-situ pollutant measurement during occupation
9.04 | In-situ measurement of CO2 and relative humidity
9.05 | Carry out a radon test

## 4.1 L1 IEQ Statement
Ind. 4.1 Levels L1
Level 1 design concept | Brief description | Addressed? (yes/no) | How has it been incorporated into the building design concept? (provide a brief description)
1.Consider how the building will be used and the expectations level of the future occupants | The expected use patterns for the building should be considered in order to identify how much ventilation needs may vary during the day or week. According to the EN 16798-1 category system, there are four expectation levels about indoor environmental quality (I, II, III and IV, with category I being highest expectations and IV being the lowest). Higher expectations translate into better control of IAQ and lower levels of pollutants but also generally higher energy consumption.
2. A basic understanding of the main pollutants in indoor air, their sources and how they might be minimised. | Try to minimise the indoor generation of air pollutants (e.g. off-gassing of VOCs from fit out materials or insulation) by the choice of low-emission materials. Assess the outdoor air quality and the potential intake of particulate and gaseous pollutants to the ventilation system. Carefully plan the building project to address any identified existing problems relating to air quality in the case of a renovation project. During construction the ingress of damp into the building fabric should be controlled and a drying out period allowed for.
3. Preferred ventilation strategy (in the context of planned use of different building zones). | Consider specific areas where IAQ can be most compromised (e.g. cooking areas, bathrooms, smoking areas, low-ceiling meeting rooms with occasionally high occupation densities, printing rooms etc.) and whether running a separate exhaust, for defined time periods, with a high specific ventilation rate would be desirable. The purpose of separate (and higher) ventilation rates should be defined (e.g. to limit CO2 increases, to minimise risk of mould growth or to minimise negative occupant perception).
4. Localised ventilation strategies to control point sources in parts of the building. | When assessing whether or not to have vegetated areas at the building site, consider how the following aspects can reduce irrigation water demand: - the choice of low water demand plants - the use of efficient irrigation techniques - staging of vegetation and other factors that can create microenvironments that reduce evaporation rates.
5. The importance of in-situ monitoring | Will the ventilation strategy be linked to real-life monitoring of IAQ and the ventilation rate? For example, with real time monitoring of duct flow, of CO2 or relative humidity in office spaces? Will periodic monitoring of VOC and particulate emissions be undertaken? If so, consider the most representative locations to install sensors/take measurements.
Adapted from Level(s) indicator 4.1: Indoor Air Quality User manual: introductory briefing, instructions and guidance (Publication version 1.1)
available at | https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents
Full manual: | https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-02/UM3_Indicator_4.1_v1.1_37pp.pdf

## 4.1 IEQ Report
Ind. 4.1 Levels L2
Use the Level(s) indoor air quality excel template for logging relevant indoor air quality estimates (L2), or measurements (L3) available at the below link:
https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-01/UM3_indicator_4.1_excel.xlsx
Full instructions are given in Levels indicator 4.1 Indoor Air Quality Manual:
https://susproc.jrc.ec.europa.eu/product-bureau/sites/default/files/2021-02/UM3_Indicator_4.1_v1.1_37pp.pdf
All Level(s) manuals available at:
https://susproc.jrc.ec.europa.eu/product-bureau/product-groups/412/documents

## Work Stages (Hidden) (hidden)
Regions Pathway Mapping
Global | Europe | UK [RIBA] | UK [PAS 2080] | France | Italy | Spain | USA | Canada | NZ (Aotearoa) | Australia
APM | ACE | RIBA Plan of Works 2020 | PAS 2080 | Ordre des Architectes | Codice appalti (D.Lgs 36/2023) | COAM | AIA | RAIC | NZCIC | NATSPEC
Stage 0 [Pre-design] - APM 0 [Strategy] | Stage 0 [Pre-design] - ACE 0 [Strategy] | Stage 0 [Pre-design] - RIBA 0 [Strategic Definition] | Stage 0 [Pre-design] - PAS 2080 [Need] | Stage 0 [Pre-design] - ODA [AOD] | Stage 0 [Pre-design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 0 [Pre-design] - COAM [Estudios Previos] | Stage 0 [Pre-design] - AIA [Pre-design] | Stage 0 [Pre-design] - RAIC [Not referenced] | Stage 0 [Pre-design] - NZCIC [Pre Design] | Stage 0 [Pre-design] - NATSPEC [Establishment]
Stage 1 [Pre-design] - APM 1 [Outcome Definition] | Stage 1 [Pre-design] - ACE 1 [Initiation] | Stage 1 [Pre-design] - RIBA 1 [Preparation & Briefing] | Stage 1 [Pre-design] - PAS 2080 [Need] | Stage 1 [Pre-design] - ODA [PRE/ESQ] | Stage 1 [Pre-design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 1 [Pre-design] - COAM [Estudios Previos] | Stage 1 [Pre-design] - AIA [Pre-design] | Stage 1 [Pre-design] - RAIC [Pre Design] | Stage 1 [Pre-design] - NZCIC [Pre Design] | Stage 1 [Pre-design] - NATSPEC [Establishment]
Stage 2 [Design] - APM 2 [Feasibility] | Stage 2 [Design] - ACE 2.1 & 2.2 [Concept & Preliminary Design] | Stage 2 [Design] - RIBA 2 [Concept Design] | Stage 2 [Design] - PAS 2080 [Optioneering] | Stage 2 [Design] - ODA [APS] | Stage 2 [Design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 2 [Design] - COAM [Proyecto Básico] | Stage 2 [Design] - AIA [Schematic Design] | Stage 2 [Design] - RAIC [Schematic Design] | Stage 2 [Design] - NZCIC [Concept & Preliminary Design] | Stage 2 [Design] - NATSPEC [Concept Design & Schematic Design]
Stage 3 [Design] - APM 3 [Concept Design] | Stage 3 [Design] - ACE 2.3 [Developed Design] | Stage 3 [Design] - RIBA 3 [Schematic Design] | Stage 3 [Design] - PAS 2080 [Design] | Stage 3 [Design] - ODA [ADP & DPC] | Stage 3 [Design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 3 [Design] - COAM [Proyecto Básico] | Stage 3 [Design] - AIA [Design Development] | Stage 3 [Design] - RAIC [Construction Documents] | Stage 3 [Design] - NZCIC [Developed Design] | Stage 3 [Design] - NATSPEC [Design Development]
Stage 4 [Design] - APM 4 [Detailed Design] | Stage 4 [Design] - ACE 2.4 [Detailed Design] | Stage 4 [Design] - RIBA 4 [Technical Design] | Stage 4 [Design] - PAS 2080 [Design] | Stage 4 [Design] - ODA [PRO & DCE] | Stage 4 [Design] - Codice appalti (D.Lgs 36/2023) [Progetto Esecutivo] | Stage 4 [Design] - COAM [Proyecto de Ejecución] | Stage 4 [Design] - AIA [Construction Documents] | Stage 4 [Design] - RAIC [Construction Procurement] | Stage 4 [Design] - NZCIC [Detailed Design] | Stage 4 [Design] - NATSPEC [Contract Documentation]
Stage 5 [Construct] - APM 5 [Delivery] | Stage 5 [Construct] - ACE 3 [Construction] | Stage 5 [Construct] - RIBA 5 [Manufacture & Construction] | Stage 5 [Construct] - PAS 2080 [Delivery] | Stage 5 [Construct] - ODA [MDT, VISA & DET] | Stage 5 [Construct] - Codice appalti (D.Lgs 36/2023) [Esecuzione Iavori] | Stage 5 [Construct] - COAM [Dirección de Obra] | Stage 5 [Construct] - AIA [Construction Administration] | Stage 5 [Construct] - RAIC [Construction Contract Administration and Field Review] | Stage 5 [Construct] - NZCIC [Construction] | Stage 5 [Construct] - NATSPEC [Construction]
Stage 6 [Handover] - APM 6 [Project Close] | Stage 6 [Handover] - ACE [Not referenced] | Stage 6 [Handover] - RIBA 6 [Handover] | Stage 6 [Handover] - PAS 2080 [Delivery] | Stage 6 [Handover] - ODA [AOR & DOE] | Stage 6 [Handover] - Codice appalti (D.Lgs 36/2023) [Collaudo & Conclusione] | Stage 6 [Handover] - COAM [Liquidación y Recepción] | Stage 6 [Handover] - AIA [Construction Administration] | Stage 6 [Handover] - RAIC [Take-over Procedures, Comissioning and Post-occupancy Evaluation] | Stage 6 [Handover] - NZCIC [Not referenced] | Stage 6 [Handover] - [Not referenced]
Stage 7 [In Use] - APM 7 [Benefits Realisation] | Stage 7 [In Use] - ACE 4 [Building Use] | Stage 7 [In Use] - RIBA 7 [Use] | Stage 7 [In Use] - PAS 2080 [Operation] | Stage 7 [In Use] - ODA [Exploitation du bâtiment] | Stage 7 [In Use] - Codice appalti (D.Lgs 36/2023) [Funzionalita] | Stage 7 [In Use] - COAM [Liquidación y Recepción] | Stage 7 [In Use] - AIA [Not referenced] | Stage 7 [In Use] - RAIC [Take-over Procedures, Comissioning and Post-occupancy Evaluation] | Stage 7 [In Use] - NZCIC [Operate] | Stage 7 [In Use] - NATSPEC [Operate]
Stage 8 [End of life] - APM 7 [Benefits Realisation] | Stage 8 [End of life] - ACE 5 [End of Life] | Stage 8 [End of life] - RIBA [Not referenced] | Stage 8 [End of life] - PAS 2080 [Purppose/ Performance Review] | Stage 8 [End of life] - ODA [Fin di vie] | Stage 8 [End of life] - Codice appalti (D.Lgs 36/2023) [Dismissione] | Stage 8 [End of life] - COAM [Not referenced] | Stage 8 [End of life] - AIA [Not referenced] | Stage 8 [End of life] - RAIC [Not referenced] | Stage 8 [End of life] - NZCIC [Not referenced] | Stage 8 [End of life] - NATSPEC [Not Referenced]
Note on B2: ====== ID#AAABQH0EOps tc={5DE7730C-CEED-450F-97DD-3CF7F7D71C23} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Please lockdown and hide this tab